## Marketing Plan Data
Marketing Plan Data
Status Color Legend & Toggle
[6 empty] | Not Started | In Progress | Delayed | Complete | Custom 1 | Custom 2 | Custom3 | Custom4
Go toList Data | [5 empty] | ON | ON | ON | ON | ON | ON | ON | ON
Task | Status | Owner | Assigned to | Anticipted start date | Anticipted start date2 | Actual start Date | Actual end Date | Estimated cost | Actual cost
Product Analysis | Not Started | Amit | Abhishek | 2024-07-01 | 2024-08-01 | 2024-06-28 |  | 1500 | 1250
Design Storyboards | In Progress | Deepak | Shivansh | 2024-07-15 | 2024-08-15 | 2024-07-13 |  | 2000 | 1840
Review Storyboard Design | Delayed | Abhishek | Shivansh | 2024-08-01 | 2024-08-20 |  |  | 1450
Research Analysis Phase I | Complete | Deepak | Vishal | 2024-06-01 | 2024-07-01 | 2024-06-01 | 2024-06-28 | 3000 | 3200
Advertising Content Creation Phase I | Custom 1 | Sahil | Mohan | 2024-09-01 | 2024-09-15 |  |  | 500
Product Requirement Definitions | Custom 2 | Abhishek | Vishal |  |  |  |  | 575 | 125
Prototype Development Specifications | Custom 3 | Shivam | Mohan | 2024-09-12 | 2024-09-25 |  |  | 1750
Quality Control, Progress Reports | Custom 4 | Vishal | Sahil | 2024-07-01 | 2024-10-01 | 2024-07-01 |  | 925 | 250
Create Storyboards | Not Started |  |  | 2024-07-15 | 2024-08-15 | 2024-07-13 |  | 2000 | 1840
Review Storyboards with Graphic Artists | Delayed | Mohan | Deepak | 2024-08-01 | 2024-08-20 |  |  | 1450
Research Analysis Phase II | Complete | Vishal | Deepak | 2024-06-01 | 2024-07-01 | 2024-06-01 | 2024-06-28 | 3000 | 3200
Advertising Content Creation Phase II | Not Started | Mohan | Amit | 2024-09-01 | 2024-09-15 |  |  | 500

## List Data
Marketing Plane Lists
Go to Marketing Plan Data
Name | Title
Vishal | Marketing Specialist
Shivam | Marketing Manager
Deepak | Project Manager
Abhishek | Marketing Analyst
Amit | Research Coordinator
Shivansh | Marketing Specialist
Sahil | Marketing Analyst
Mohan | Associate Marketing Manager